## Sheet1
DATE | Time | Mode | mode | Comments |  | LOG entry
C1
20000829 | 21:14
Voltage monitor registered 6.067 V (5.688-6.211 V nominal).
Temperature monitor registered 23.2 deg. C.
All other monitored housekeeping parameters
registered their default values.
20000908 | 03:50 - 04:05 | BM2 | (Burst) |  |  | Y
Some weak AKR was observed in the 125 and 250 kHz
conversion modes.
Expected interference was observed at the battery
converter frequency (65 kHz) and it harmonics, and
at the spacecraft power converter frequency (131
kHz) and its harmonics. This interference is no
more than 3 dB above the background noise level.
20000908 | 10:14 - 10:44 | TDA | -8 (DSN) |  |  | N
Attempt failed; attributed to miscommunication
between ESOC and DSN.
20000921 | 02:14 - 02:44 | BM2 | (Burst) | Second burst mode data acquisition attempt successful. |  | N
20000923 | 07:39 - 07:54 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | Y
20000928 | 02:45 - 03:00 | BM2 | (Burst) | Fourth burst mode data acquisition attempt successful. |  | Y
20000930 | 08:35 - 08:50 | BM2 | (Burst) | Fifth burst mode data acquisition from SC1 successful. |  | N
20001006 | 05:02 - 05:20 | BM2 | (Burst) |  |  | Y
20001008 | 12:09 - 12:29 | BM2 | (Burst) | Seventh burst mode data acquisition from SC1 successful. |  | Y
20001009 | 00:08 - 00:28 | BM2 | (Burst) | Eighth burst mode data acquisition from SC1 successful. |  | Y
20001010 | 01:08 - 01:28 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | Y
20001010 | 01:38 - 01:58 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | Y
20001011 | 08:00 - 08:10 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | Many
20001016 | 02:00 - 04:01 | TDA | -8 (DSN) | Second DSN data acquisition attempt from SC1 successful. |  | N
20001127 | 12:49 - 13:49 | BM2 | (DSN) |  |  | N
SC1, SC2, SC3, SC4, successful for SC1, SC2, and
SC3, failed for SC4.
Access Data Files <http://www-pw.physics.uiowa.edu/plasma-wave/istp/cluster/commissioning/c1>
C2
20000829 | 2:01
Voltage monitor registered 6.118 V (5.688-6.211 V nominal).
Temperature monitor registered 24.4 deg. C.
All other monitored housekeeping parameters
registered their default values.
20000905 | 23:55 - 00:10 | BM2 | (Burst) |  |  | Y
converter frequency (65 kHz) and its harmonics,
and at the spacecraft power converter frequency
(131 kHz) and its harmonics. This interference
is no more than 3 dB above the background noise
level.
20000906 | 01:15 - 01:45 | TDA | -8 (DSN) |  |  | N
successful. Observed nonperiodic, "S or hook-
shaped" emissions in the range 2-4 kHz, which is
above fce. The slopes of the central part of the
S or hook varied.
20000914 | 14:02 - 14:17 | BM2 | (Burst) | Observed very intense partial sinusoidal emissions |  | Y
at half the spin rate. The source of this
interference is still under investigation.
20000921 | 17:20 - 17:35 | BM2 | (Burst) | Observed the "S or hook-shaped" emissions at |  | Y
0.4 - 2 kHz.
20000923 | 07:39 - 07:54 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | Y
20000928 | 19:44 - 19:59 | BM2 | (Burst) | Fifth burst mode data acquisition from SC2 successful. |  | Y
20001006 | 05:02 - 05:20 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | Y
20001010 | 01:08 - 01:28 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | Y
20001018 | 01:38 - 01:58 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | N
20001011 | 08:00 - 08:10 | BM2 | (Burst) | Simultaneous data acquisition from SC1 and SC2. |  | Many
20001011 | 10:58 - 13:03 | TDA | -8 (DSN) | Second DSN data acquisition attempt from SC2 successful. |  | N
20001127 | 12:49 - 13:49 | BM2 | (DSN) |  |  | N
SC1, SC2, SC3, SC4, successful for SC1, SC2, and
SC3, failed for SC4.
Access Data Files <http://www-pw.physics.uiowa.edu/plasma-wave/istp/cluster/commissioning/c2>
_WBD F7 on | SC3_
DATE
20001009 | 10:38
Voltage monitor registered 6.057 V (5.688-6.211 V nominal).
Temperature monitor registered 20.4 deg. C.
All other monitored housekeeping parameters
registered their default values.
20001012 | 00:06 - 00:25 | BM2 | (Burst) |  |  | Y
Some strong AKR was observed in the 125 and
250 kHz conversion modes. Also some continuum was
observed, as well as some narrowband emissions at
750 Hz and 1.2kHz (probably electron cyclotron
emissions). Expected interference was observed at
the battery converter frequency (65 kHz) and its
harmonics, and at the spacecraft power converter
frequency (131 kHz) and its harmonics. This
interference is no more than 3 dB above the
background noise level.
20001012 | 06:26 - 07:00 | TDA | -8 (DSN) |  |  | N
20001013 | 07:26 - 07:42 | BM2 | (Burst) |  |  | Y
20001018 | 01:38 - 01:58 | BM2 | (Burst) | Third burst mode data acquisition attempt successful. |  | Y
20001024 | 04:08 - 04:28 | BM2 | (Burst) |  |  | Y
20001027 | 14:04 - 14:24 | BM2 | (Burst) |  |  | Y
20001116 | 08:20 - 08:40 | BM2 | (Burst) |  |  | Y
20001127 | 12:49 - 13:49 | BM2 | (DSN) |  |  | N
SC1, SC2, SC3, SC4, successful for SC1, SC2, and
SC3, failed for SC4.
Access Data Files <http://www-pw.physics.uiowa.edu/plasma-wave/istp/cluster/commissioning/c3>
_WBD F8 on | SC4_
DATE
20001023 | 19:16
Voltage monitor registered 5.965 V (5.688-6.211 V nominal).
Temperature monitor registered 20.8 deg. C.
All other monitored housekeeping parameters
registered their default values.
20001025 | 23:20 - 23:40 | BM2 | (Burst) |  |  | Y
20001027 | 14:04 - 14:24 | BM2 | (Burst) |  |  | Y
20001101 | 08:14 - 08:34 | BM2 | (Burst) |  |  | Y
20001104 | 07:59 - 08:31 | TDA | -8 (DSN) |  |  | N
20001106 | 03:28 - 03:48 | BM2 | (Burst) |  |  | Y
20001110 | 20:42 - 21:00 | BM2 | (Burst) |  |  | Y
20001114 | 03:18 - 03:38 | BM2 | (Burst) |  |  | Y
20001117 | 23:57 - 00:17 | BM2 | (Burst) |  |  | Y
20001121 | 23:45 - 00:05 | BM2 | (Burst) |  |  | Y
20001125 | 03:40 - 04:00 | BM2 | (Burst) |  |  | Y
20001127 | 12:49 - 13:49 | BM2 | (DSN) |  |  | N
SC1, SC2, SC3, SC4, successful for SC1, SC2, and
SC3, failed for SC4.
20001128 | 05:15 - 07:16 | TDA | -8 (DSN) |  |  | N
20001201 | 09:20 - 09:38 | BM2 | (Burst) |  |  | Y